## Plan
Milestone | Description | Type | Expected Estimate(hours) | Release Date | Actual Date
Go Fundamentals | Tour of Go | interactive | 4 | 2021-04-01 14:51
| Rob Pike - Simplicity is Complicated | video | 0.5 | 2021-04-01 14:51
| The Zen of Go | article | 1 | 2021-04-01 14:51
| Go proverbs | video | 0.5 | 2021-04-01 14:51
| Go by Example | tutorial | 10 | 2021-04-05 14:51
| Basic types | article | 2 | 2021-04-06 14:51
| Strings in Go | article | 3 | 2021-04-06 14:51
| Francesc Campoy - Understanding nil | video | 2 | 2021-04-06 14:51
| 5 Useful Ways to Use Closures | article | 2 | 2021-04-07 14:51
| Utility "Tree" | task | 8 | 2021-04-08 14:51
| Go Slices: usage and internals | article | 1 | 2021-04-08 14:51
| Go maps in action | article | 1 | 2021-04-08 14:51
| Word Count | task | 2 | 2021-04-08 14:51
| Arrays, slices (and strings): The mechanics of 'append' | article | 2 | 2021-04-08 14:51
| Methods, Interfaces and Embedded Types in Go | article | 1 | 2021-04-09 14:51
| Copying Interface Values In Go | article | 1 | 2021-04-10 14:51
| Volume Calculator | task | 4 | 2021-04-10 14:51
| Anatomy of Modules in Go | article | 3 | 2021-04-13 14:51
| Exported/Unexported Identifiers In Go | article | 1 | 2021-04-14 14:51
| Error handling and Go | article | 1 | 2021-04-14 14:51
| Defer, Panic, and Recover | article | 1 | 2021-04-14 14:51
| Concurrency, Goroutines and GOMAXPROCS | article | 1 | 2021-04-14 14:51
| The Behavior Of Channels | article | 1 | 2021-04-14 14:51
| Kavya Joshi - Understanding Channels | video | 1 | 2021-04-14 14:51
| Why are there nil channels in Go? | video | 1 | 2021-04-14 14:51
| Illustrated Tales of Go Runtime Scheduler | article | 3 | 2021-04-15 14:51
| Generating code | article | 2 | 2021-04-15 14:51
| JSON and Go | article | 1 | 2021-04-15 14:51
| SemVer | article | 1 | 2021-04-15 14:51
| 50 shades of Go | article | 3 | 2021-04-16 14:51
| Context package | video | 4 | 2021-04-16 14:51
Go HTTP | REST on wiki | article | 0.5 | 2021-04-16 14:51
| HTTP Status Codes | documentation | 1 | 2021-04-16 14:51
| REST Philosophy | article | 0.5 | 2021-04-16 14:51
| REST API Best Practices | article | 0.5 | 2021-04-16 14:51
| REST JSON API design principles | article | 0.5 | 2021-04-19 14:51
| HTTP methods in REST APIs | article | 0.5 | 2021-04-20 14:51
| Context package | video | 1 | 2021-04-20 14:51
| Implement REST API | task | 24 | 2021-04-26 14:51
| Testing HTTP servers in Go | video | 1 | 2021-04-26 14:51
| Unit test HTTP server | task | 16 | 2021-04-27 14:51
| Gorilla mux | documentation | 2 | 2021-04-27 14:51
| Testify | documentation | 2 | 2021-04-27 14:51
| Add packages | task | 16 | 2021-04-28 14:51
| HTTP middleware | article | 2 | 2021-04-29 14:51
| Add HTTP middleware | task | 8 | 2021-04-30 14:51
Go Code Quality | Effective Go | article | 2 | 2021-04-30 14:51
| Go best practices | video | 1 | 2021-04-30 14:51
| Organizing Go code | article | 0.5 | 2021-04-30 14:51
| Standard package layout | article | 1 | 2021-04-30 14:51
| Building WTF Dial | article | 4 | 2021-05-03 14:51
| Code Refactoring | task | 24 | 2021-05-04 14:51
| Go modules | article | 3 | 2021-05-04 14:51
| Add Dependencies | task | 4 | 2021-05-05 14:51
| Godoc: documenting Go code | article | 0.5 | 2021-05-06 14:51
| Go fmt your code | article | 0.5 | 2021-05-06 14:51
| Goimports | article | 0.5 | 2021-05-06 14:51
| Meta Linter | article | 0.5 | 2021-05-06 14:51
| Add linters | task | 8 | 2021-05-07 14:51
| OpenAPI 3.0 | article | 3 | 2021-05-07 14:51
| Add API documentation | task | 8 | 2021-05-10 14:51
| Makefile | article | 0.5 | 2021-05-10 14:51
| Create makefile | task | 3 | 2021-05-11 14:51
Git | Git book Stage 1 | documentation | 10 | 2021-05-12 14:51
| Git book Stage 2 | documentation | 10 | 2021-05-13 14:51
| Git book videos | video | 1 | 2021-05-13 14:51
| Git Best Practices:Workflow Guidelines | article | 1 | 2021-05-13 14:51
| Git Guidelines and Best Practices | article | 1 | 2021-05-13 14:51
| Git Feature Branch Workflow | documentation | 1 | 2021-05-14 14:51
| Gitflow Workflow | documentation | 1 | 2021-05-14 14:51
| About pull requests | documentation | 1 | 2021-05-14 14:51
| Merging vs. Rebasing | documentation | 1 | 2021-05-14 14:51
| Git Feature Branch Workflow | task | 10 | 2021-05-17 14:51
| Git Branching | interactive | 1 | 2021-05-17 14:51
Database Fundamentals | How databases are arranged | video | 2 | 2021-05-18 14:51
| Relational Database Concepts | video | 0.5 | 2021-05-18 14:51
| What is NoSQL? | article | 0.5 | 2021-05-18 14:51
| NoSQL database types | article | 0.5 | 2021-05-18 14:51
| Key-Value database | article | 0.5 | 2021-05-18 14:51
| Document store database | article | 0.5 | 2021-05-18 14:51
| Column Store database | article | 0.5 | 2021-05-18 14:51
| Graph database | article | 0.5 | 2021-05-18 14:51
| Reasons to use RDBMS | article | 0.5 | 2021-05-18 14:51
| RDBMS vs DBMS | article | 0.5 | 2021-05-18 14:51
| CAP-theorem | video | 1 | 2021-05-18 14:51
| CAP PACELC BASE ACID in short | article | 0.5 | 2021-05-18 14:51
Database NoSQL Fundamentals | Introduction to NoSQL | video | 1 | 2021-05-18 14:51
| The basics of NoSQL | article | 1 | 2021-05-19 14:51
| Redis Crash Course Tutorials | video | 1 | 2021-05-19 14:51
| Redis Documentation | documentation | 3 | 2021-05-19 14:51
Database SQL Fundamentals | Transact-SQL Reference | documentation | 16 | 2021-05-24 14:51
| Transact-SQL Tutorial | video | 16 | 2021-05-25 14:51
| A Visual Explanation of SQL Joins | article | 2 | 2021-05-25 14:51
| Postgre SQL Tutorial | video | 4 | 2021-05-26 14:51
| PostgreSQL Manuals | documentation | 24 | 2021-06-01 14:51
| PostgreSQL JSON | documentation | 2 | 2021-06-01 14:51
| Medical Research | task | 24 | 2021-06-07 14:51
| Update Great Star Financial Profile | task | 16 | 2021-06-08 14:51
| Requests to JSON | task | 12 | 2021-06-09 14:51
Clean code | Main Principles | documentation | 1 | 2021-06-09 14:51
| Technical debt | documentation | 1 | 2021-06-09 14:51
| When to refactor | documentation | 1 | 2021-06-09 14:51
| How to refactor | documentation | 1 | 2021-06-09 14:51
| Types of bad code | documentation | 6 | 2021-06-10 14:51
| Methods of refactoring | documentation | 6 | 2021-06-11 14:51
| Best Practices | article | 1 | 2021-06-11 14:51
| Clean Code Summary and Key Points | article | 1 | 2021-06-11 14:51
| JavaScript Clean Code - Best Practices | article | 1 | 2021-06-11 14:51
| 13 Simple Rules for Good Coding | article | 1 | 2021-06-11 14:51
| Good Code vs Bad Code | article | 1 | 2021-06-11 14:51
| Why, what, where. Kinds of testing | article | 1 | 2021-06-11 14:51
| Rules of naming | article | 1 | 2021-06-11 14:51
| Naming convention | article | 1 | 2021-06-14 14:51
| Development Principles | tutorial | 1 | 2021-06-14 14:51
| Design principles | article | 1 | 2021-06-14 14:51
| Optimization | tutorial | 4 | 2021-06-14 14:51
| Mess Code | task | 1 | 2021-06-14 14:51
| Grid bad code | task | 1 | 2021-06-15 14:51
| Naming domain person | task | 0.5 | 2021-06-15 14:51
Docker | Docker Docs | documentation | 16 | 2021-06-16 14:51
| Docker Curriculum | tutorial | 16 | 2021-06-21 14:51
| Docker Tutorial for Beginners | video | 3 | 2021-06-21 14:51
| Docker Containers Full Course | video | 3 | 2021-06-21 14:51
| MySQl Container | task | 4 | 2021-06-22 14:51
| Own Image | task | 6 | 2021-06-23 14:51
Agile | Agile Manifesto | article | 0.5 | 2021-06-23 14:51
| Scrum | documentation | 2 | 2021-06-23 14:51
| Kanban | documentation | 2 | 2021-06-23 14:51
| Agile & Scrum - Introduction | video | 2 | 2021-06-23 14:51
| Kanban for teams | video | 1 | 2021-06-24 14:51
| Effective 1-on-1 | video | 1 | 2021-06-24 14:51
| Zen Retrospective | video | 1 | 2021-06-24 14:51
| How to screw up the team work | video | 1 | 2021-06-24 14:51
| Sprint Planning | task | 8 | 2021-06-25 14:51
| 1-on-1 meeting | task | 4 | 2021-06-25 14:51
| Sprint Retrospective | task | 6 | 2021-06-28 14:51